## Summary
FAE SR REPORT — DEPARTMENT SUMMARY (01–22 JUL 2026)
DEPARTMENT | CLOSED | PENDING | TOTAL
Civil | 30 | 229 | 259
Electrical | 13 | 52 | 65
Mechanical | 34 | 164 | 198
TOTAL | 77 | 445 | 522
Notes:
• Mechanical includes all plumbing issues (plumbing falls under Mechanical).
• Source: FAE SR Report dated 22.07.26 (period 01–22 Jul 2026). Status reflects that report:
OPEN → PENDING, CLOSED → CLOSED.
• Departments for 01–09 Jul reuse the prior analysis' classification; 10–22 Jul are
classified from the item description.

## Daily Breakdown
DATE | Civil | Electrical | Mechanical | TOTAL
01.07.26 | 10 | 3 | 6 | 19
02.07.26 | 14 | 4 | 11 | 29
03.07.26 | 18 | 2 | 10 | 30
04.07.26 | 9 | 1 | 12 | 22
05.07.26 | 10 | 2 | 10 | 22
06.07.26 | 23 | 3 | 6 | 32
07.07.26 | 10 | 2 | 5 | 17
08.07.26 | 17 | 6 | 9 | 32
09.07.26 | 22 | 5 | 6 | 33
10.07.26 | 9 | 4 | 8 | 21
11.07.26 | 9 | 0 | 6 | 15
12.07.26 | 15 | 1 | 6 | 22
13.07.26 | 4 | 6 | 17 | 27
14.07.26 | 7 | 2 | 9 | 18
15.07.26 | 7 | 3 | 13 | 23
16.07.26 | 18 | 1 | 5 | 24
17.07.26 | 7 | 6 | 10 | 23
18.07.26 | 8 | 5 | 5 | 18
19.07.26 | 13 | 3 | 10 | 26
20.07.26 | 16 | 4 | 21 | 41
21.07.26 | 3 | 2 | 6 | 11
22.07.26 | 10 | 0 | 7 | 17
TOTAL | 259 | 65 | 198 | 522

## Detail
SHEET | SL NO | LOCATION | DESCRIPTION | SR NO | DEPARTMENT | STATUS
01.07.26 | 1 | FAE | Blvd Mwr 1St Cubicle Hole Cove Missing | 103024342 | Civil | PENDING
01.07.26 | 2 | FAE | Blvd Fwr #2 Cubicle Washbasin Require Silicon |  | Mechanical | CLOSED
01.07.26 | 3 | FAE | Blvd Fwr Entrance Up Ceiling Requires Painting | 103034743 | Civil | CLOSED
01.07.26 | 4 | FAE | Sf Fpr Ablution Lhs #8 Water Tap Wall Steal Frame Is Out Needs To Fixed | 103034963 | Mechanical | PENDING
01.07.26 | 5 | FAE | Sf Fpr Second Door Entrance Door Frame Has Rust Needs To Paint | 103034996 | Civil | PENDING
01.07.26 | 6 | FAE | Sf Fpr #1 Door Main Entrance Light Frame Is Cracked Needs To Fixed | 103034997 | Electrical | PENDING
01.07.26 | 7 | FAE | Sf Fpr Shoe Rack Area Upper Ceiling Fire Sprinkler Head Needs To Fixed Properly | 103032236 | Mechanical | PENDING
01.07.26 | 8 | FAE | 3Rd Floor Pe-05/06 Lobby Ac Grills Painting Required Please | 103034920 | Mechanical | PENDING
01.07.26 | 9 | FAE | Gf Gina Mwr Inside The Janitor Room Drainage Overflying Need To Rectify Please | 103035339 | Mechanical | CLOSED
01.07.26 | 10 | FAE | Gf Tods Fwr Lhs #6 Cubicle Wooden Frame Is Chip |  | Civil | PENDING
01.07.26 | 11 | FAE | 3Rd Fl Fwr Entrance Tiles Grouting Requirements |  | Civil | PENDING
01.07.26 | 12 | FAE | 3Rd Fl Entrance Door Frame Paint Chipped |  | Civil | PENDING
01.07.26 | 13 | FAE | Gf Staff Mwr Urinal Water Senser Not Working | 103051612 | Electrical | CLOSED
01.07.26 | 14 | FAE | Gf Gina Mwr From Pod 3Rd Cubicle Skirting Grout Missing | 103051898 | Civil | CLOSED
01.07.26 | 15 | FAE | Blvd Front Of Hermes Ceiling Acess Panel Corners Chipped | 103051640 | Civil | CLOSED
01.07.26 | 16 | FAE | 1F P5 Beside Fire Hose Cabinet Wall Water Leaking Need Assistance | 103053190 | Mechanical | PENDING
01.07.26 | 17 | FAE | Blvd Mwr Front Of Janitor Room Cubicle Skirting Not Fixed Properly | 103053249 | Civil | CLOSED
01.07.26 | 18 | FAE | Gf Staff Mwr Urinal Water Senser Not Working | 103051612 | Electrical | CLOSED
01.07.26 | 19 | FAE | Gf Vip Mwr Rhs 3Rd Cubicle Door Frame Chipped | 103057537 | Civil | CLOSED
02.07.26 | 1 | FAE | Fae, Basement Boh Near B1-St-18 Store Fire Extinguisher Door Need To Paint Touch Up | 103063841 | Civil | CLOSED
02.07.26 | 2 | FAE | Fae, Basement Boh Near Fwr Fire Extinguisher Door Need To Paint Touch Up | 103064024 | Civil | CLOSED
02.07.26 | 3 | FAE | Fae, Basement Boh B1.M.08 Emaar Store Door And Door Farm Need To Paint Touch Up | 103064150 | Civil | CLOSED
02.07.26 | 4 | FAE | Fae Vip Lounge Staircase 49A Wall Paint Coming Out | 103064628 | Civil | PENDING
02.07.26 | 5 | FAE | Fae 4F Fwr #1 Cubicle Hand Shattaf Is Broken |  | Mechanical | PENDING
02.07.26 | 6 | FAE | Fae Ff Beside Repossi The Lock Of The Green Dress Art Glass Door Needs To Be Changed | 103076611 | Civil | CLOSED
02.07.26 | 7 | FAE | Fae Sf Perfume Area Dior Shop Ceiling Water Dropping. | 103084846 | Mechanical | CLOSED
02.07.26 | 8 | FAE | Fae Sf Perfume Area Lv Shop Front Of Ceiling Water Dripping. | 103084847 | Mechanical | CLOSED
02.07.26 | 9 | FAE | Fae Ff Highend Fwr Wb # Lhs # No. 2 Handsoap Sensor Nor Working. | 103084875 | Electrical | PENDING
02.07.26 | 10 | FAE | Fae, Gf Gina Mwr Urinal Side Skirting Corner Grout Missing | 103085010 | Mechanical | CLOSED
02.07.26 | 11 | FAE | Fae, Gf Gina Mwr Urinal Side Skirting Corner Grout Missing | 103085009 | Mechanical | PENDING
02.07.26 | 12 | FAE | Fae 2F Above Novikov Restaurant Seating Area Ceiling Seepage Need Paint Touchup | 103085613 | Mechanical | PENDING
02.07.26 | 13 | FAE | Fae, Gf Gina Mwr Boh Riser 14 Floor Joint Silicone Is Detached | 103086072 | Mechanical | PENDING
02.07.26 | 14 | FAE | Fae, Blvd Sliding Door Require Paint Touch Up Pls | 103086105 | Civil | PENDING
02.07.26 | 15 | FAE | Fae Sf Mlb Fwr Janitor Door Frame Ans Wall Gap Need To Fix. | 103086853 | Civil | PENDING
02.07.26 | 16 | FAE | Fae Sf Mlb Fwr Wb #Vno .3 Bin Liner Need To Fix | 103086920 | Civil | PENDING
02.07.26 | 17 | FAE | Fae / Sf Mlb Fpyr Ablution Last One Wall Steel Frame Need To Fix. | 103087002 | Civil | CLOSED
02.07.26 | 18 | FAE | Fae / Sf Mlb Fwr Janitor Room Noisy Sound Coming. | 103087123 | Mechanical | PENDING
02.07.26 | 19 | FAE | Fae / Sf Mlb Fwr Most Of Cubical Silicone Requirements. | 103087153 | Mechanical | PENDING
02.07.26 | 20 | FAE | Fae, Sf Perfumery Area Ceiling Is Damaged | 103087328 | Civil | PENDING
02.07.26 | 21 | FAE | Fae 4Th Fl Washroom Corridor Emergency Light Cover Broken. |  | Electrical | PENDING
02.07.26 | 22 | FAE | Fae, Gf Vip Mwr Lhs 1St Cubicle Water Tap Leakage | 103088359 | Mechanical | CLOSED
02.07.26 | 23 | FAE | Fae Vip Lounge Mwr Tap No 1 Shaking Needs To Fix | 103085613 | Mechanical | CLOSED
02.07.26 | 24 | FAE | Fae 3F Mwr Lhs Washbasin No 2,3,Soap Dispenser Sensor Not Working Properly | 103092510 | Electrical | CLOSED
02.07.26 | 25 | FAE | Fae 3Rd Fl Fwr Cub No.1 Door Frame Paint Chipped. | 103092858 | Civil | PENDING
02.07.26 | 26 | FAE | Fae P6 Beside The Revolving Door Pillar Bottom Wooden Part Needs To Fix | 103095474 | Civil | PENDING
02.07.26 | 27 | FAE | Fae Ff High End Mwr Wash Basin Number 5 Soap Sensor Not Working On The Right Side | 103065978 | Electrical | PENDING
02.07.26 | 28 | FAE | Fae Mlb Fpr Further End From The Ablution Entrance Stainless Steel Corner Guards Detached | 103096717 | Civil | PENDING
02.07.26 | 29 | FAE | Fae 1St Floor High-End Mwr Rhs 1No Cubicle Inside The Tissue Dispenser Steel Detached Need To Fix | 103097398 | Civil | CLOSED
03.07.26 | 1 | FAE | Fourth Floor Mwr Hk Janitor Room Ceiling Need Paint Touchup | 103100399 | Civil | PENDING
03.07.26 | 2 | FAE | Basement Staff Mwr Rhs 5No Cubicle Inside The Ceiling Discoloured Mark Need Paint Required | 103100488 | Civil | PENDING
03.07.26 | 3 | FAE | Lg Near Staff Pantry Floor Painting Required Please | 103084167 | Civil | PENDING
03.07.26 | 4 | FAE | Lg Transguard Pantry Outside Wall Need To Paint Required | 103100657 | Civil | PENDING
03.07.26 | 5 | FAE | Fourth Floor Mwr Rhs 2Nd Soap Sensor Not Working | 103084631 | Electrical | PENDING
03.07.26 | 6 | FAE | Lg Pantry Door Need To Paint Required | 103100992 | Civil | PENDING
03.07.26 | 7 | FAE | Basement Mwr Rhs 3No Cubicle Inside The Wooden Door Gap Need To Put Silicone | 103101060 | Mechanical | PENDING
03.07.26 | 8 | FAE | Basement Mwr Lhs 2No Washbasin Area Need To Put Silicone | 103101061 | Mechanical | PENDING
03.07.26 | 9 | FAE | Basement Mwr Lhs 3No Washbasin Area Need To Put Silicone | 103101061 | Mechanical | PENDING
03.07.26 | 10 | FAE | Basement Staff Mwr Maindoor Bith Side Need To Paint Required | 103101174 | Civil | PENDING
03.07.26 | 11 | FAE | Basement Staff Mwr Outside Both Side Wall Scratch Mark Need To Paint Required | 103101175 | Civil | PENDING
03.07.26 | 12 | FAE | Sf Mlb Mwr Cubicle No #5 Door Lock Broken Need To Rectified | 103101176 | Civil | CLOSED
03.07.26 | 13 | FAE | Basement Level Near Female Staff Washroom Outside Ramp Both Side Wall Need To Paint Required | 103101273 | Civil | PENDING
03.07.26 | 14 | FAE | Vip Lounge Spa Room Door Skirting Gap Need To Put Grouting | 103102316 | Civil | PENDING
03.07.26 | 15 | FAE | Vip Lounge Spa Room Washroom Entrance Door Gap Need To Put Grouting | 103102748 | Civil | PENDING
03.07.26 | 16 | FAE | Vip Lounge Spa Room Washroom Entrance Door Gap Need To Put Grouting | 103102748 | Civil | PENDING
03.07.26 | 17 | FAE | Vip Lounge Mwr 1No Cubicle Wooden Door Chipped | 103102908 | Civil | PENDING
03.07.26 | 18 | FAE | Ff He Mwr Rhs Washbasin #5 Cabinet Door Hinges Damage Need To Fixed | 103103457 | Mechanical | CLOSED
03.07.26 | 19 | FAE | Sf Fpr Lhs #2 Water Tap Cover Is Missing | 103108950 | Mechanical | CLOSED
03.07.26 | 20 | FAE | Viplounge Meeting Wb # Drain Rusty Have. | 103133760 | Civil | PENDING
03.07.26 | 21 | FAE | Viplounge Fwr Cub No.1 Door Handle Need To Touch Up. | 103133762 | Civil | PENDING
03.07.26 | 22 | FAE | Viplounge Fwr Cub No.1 Door Paint Need To Touch Up. | 103133794 | Civil | PENDING
03.07.26 | 23 | FAE | Viplounge Fwr Cub No.1 Ceiling Grouting Requirements Need To Touch Up. | 103133802 | Civil | PENDING
03.07.26 | 24 | FAE | P6 Beside The Revolving Door Pillar Bottom Wooden Wall Light Not Working |  | Electrical | PENDING
03.07.26 | 25 | FAE | Sf Mlb Fwr Cubicle Number 1Water Spray Pipe Spraying Nonstop Outside. | 103065269 | Mechanical | PENDING
03.07.26 | 26 | FAE | Sf Mlb Mwr Rhs Washbasin No 1 Until 3 Below The Mirror Grouting Need To Fill |  | Mechanical | PENDING
03.07.26 | 27 | FAE | Sf Mlb Mwr Lhs Beside And Above Washbasin No 1 Tiles Grouting Need To Fill |  | Mechanical | PENDING
03.07.26 | 28 | FAE | Sf Mlb Mwr Cubicle No 5 Wc Seat Cover Steel Part Missing | 103133873 | Mechanical | PENDING
03.07.26 | 29 | FAE | Cubicle Door Lock Needs To Be Fixed Back, 2Nd Cubicle Lhs Gf Vip Fwr Fae |  | Civil | CLOSED
03.07.26 | 30 | FAE | Sound Coming From Wc Sometimes 3Rd Cubicle Lhs Gf Vip Fwr Fae | 103136850 | Mechanical | PENDING
04.07.26 | 1 | FAE | Fae 1St Floor High-End Male Washroom Lhs 5No Washbasin Area Bin Around Need To Put Silicone | 103137089 | Mechanical | CLOSED
04.07.26 | 2 | FAE | Fae P2 Driver Mwr Washbasin 2Nd Water Dispenser Need To Rectify Please | 103150406 | Mechanical | PENDING
04.07.26 | 3 | FAE | Ae P2 Driver Mwr Washbasin Lhs Soap Dispenser Need To Rectify Please | 103150539 | Mechanical | PENDING
04.07.26 | 4 | FAE | Fae Sf Fpr Ablution Area Grouting Require | 103155219 | Civil | PENDING
04.07.26 | 5 | FAE | Fae P6 Beside The Revolving Door Pillar Bottom Wooden Wall Light Not Working | 103134416 | Electrical | PENDING
04.07.26 | 6 | FAE | Fae Tf Fwr Last Cubicle Drainage Required Grouting |  | Mechanical | PENDING
04.07.26 | 7 | FAE | Fae 1F High-End Mwr Lhs Cubicle No 5 Wc Seat Cover Not Closing Properly |  | Mechanical | PENDING
04.07.26 | 8 | FAE | Fae 4Th Fwr Last Cubicle Door Frame Chipped | 103134476 | Civil | PENDING
04.07.26 | 9 | FAE | Fae Sf Fwr Bcr No.1 Door Paint Chipped. |  | Civil | PENDING
04.07.26 | 10 | FAE | Fae Gf Tod'S Fwr 1St Cubicle Lhs Washbasin Tap Water Drips Continuously And Has Sound | 103168579 | Mechanical | CLOSED
04.07.26 | 11 | FAE | Fae Gf Tod'S Fwr Cubicle No 6# Rhs Wc Seat Cover Damage | 103168811 | Mechanical | PENDING
04.07.26 | 12 | FAE | Fae Sf Fwr Bcr No.1 Door Paint Chipped. | 103169024 | Civil | PENDING
04.07.26 | 13 | FAE | Fae 1F High-End Mwr Lhs Cubicle No 5 Wc Seat Cover Not Closing Properly | 103168147 | Mechanical | PENDING
04.07.26 | 14 | FAE | Fae, Gf Gina Mwr Wash Basin Drainage Pipe Loose Condition Pls Attend Asap |  | Mechanical | CLOSED
04.07.26 | 15 | FAE | Fae Sf Fwr Lhh# Cub No. 2 Skirting Removed Need Fix . | 103169120 | Civil | PENDING
04.07.26 | 16 | FAE | Fae Sf High-End Fwr #2 Bcr From The Entrance Sliding Door Edge Chipped | 103139529 | Civil | PENDING
04.07.26 | 17 | FAE | Fae, Basement Mwr Lhs 1St Wash Basin Water Pipe Is Leakage Pls Attend Asap | 103172484 | Mechanical | CLOSED
04.07.26 | 18 | FAE | Fae, Lg Se-01,02 Wall Corner Safety Panel Is Detached | 103172511 | Civil | PENDING
04.07.26 | 19 | FAE | Fae 1St Floor High-End Mwr Lhs 1No Cubicle Wc Flushing Button Gap Need To Put Silicone | 103174824 | Mechanical | CLOSED
04.07.26 | 20 | FAE | Fae, Tf Mwr Rhs Washbasin Area Near Skirting Need To Put Grouting | 103175737 | Mechanical | PENDING
04.07.26 | 21 | FAE | Fae, Sf Behind Pl-32 Boh Lhs Wall Need To Paint Touch Up | 103175877 | Civil | CLOSED
04.07.26 | 22 | FAE | Fae Gf Near Moynat Celling Painting Required | 103176270 | Civil | PENDING
05.07.26 | 1 | FAE | Sf Mlb Mpr Ac Is Not Colling Very Warm Need To Rectified Please | 103181166 | Mechanical | CLOSED
05.07.26 | 2 | FAE | Fae 1St Floor Common Area P5 Lobby Wall Need To Paint Required | 103184237 | Civil | PENDING
05.07.26 | 3 | FAE | Fae 3Rd Floor Mwr Bcr Washbasin Area Silicon Required | 103187944 | Mechanical | CLOSED
05.07.26 | 4 | FAE | Fae, Sf He Mwr Rhs Cubicle #5 Wc Flash Constantly Working Need To Rectified | 103185917 | Mechanical | CLOSED
05.07.26 | 5 | FAE | Fae, Tf Mwr Rhs Fast Washbasin Mountain Bin Need To Put Silicon | 103186148 | Mechanical | CLOSED
05.07.26 | 6 | FAE | Fae 2F Perfumery Area Seating Area Pillar Behind Dustbin Wall Has Permanent Stain |  | Civil | PENDING
05.07.26 | 7 | FAE | Fae 1F Welcome Court Bedide Revolving Door Behind Dustbin Wall Has Permanent Stain | 103211729 | Civil | PENDING
05.07.26 | 8 | FAE | Tg Sfm Fae Sf Mlb Fwr Pod Seat Cover Getting Loose. | 103211727 | Mechanical | PENDING
05.07.26 | 9 | FAE | Fae Sf Mlb Fwr Pod Seat Cover Getting Loose. | 103211873 | Mechanical | PENDING
05.07.26 | 10 | FAE | Fae 3F Mwr Pod Cubicle Wall Mounted Bin Key Broken | 103212162 | Civil | CLOSED
05.07.26 | 11 | FAE | Fae, Staircase 02D Steps Need To Re-Paint | 103212517 | Civil | PENDING
05.07.26 | 12 | FAE | Fae, Staircase 02A Steps Need To Re-Paint Pls | 103212530 | Civil | PENDING
05.07.26 | 13 | FAE | Fae, Gf Vip Mwr Vanity Counter Water Tap Knob Loose Condition | 103212578 | Mechanical | PENDING
05.07.26 | 14 | FAE | Fae, Vip Lounge Mwr Entrance Door Frame Is Different Color Pls Check | 103212590 | Civil | PENDING
05.07.26 | 15 | FAE | Fae Vip Lounge Lift Pl 32 Wall Grouting Required | 103186215 | Civil | PENDING
05.07.26 | 16 | FAE | Fae Sf Mlb Fwr Cub No. 3 Flush Buttom Was Properly Not Flushing. |  | Mechanical | PENDING
05.07.26 | 17 | FAE | Fae 2Nd Floor Mlb Male Washroom Lhs 1 No Washbasin Area Hand Soap Sensor Not Working | 103214486 | Electrical | CLOSED
05.07.26 | 18 | FAE | Fae Gf Apple Atrium Plant Pot Lights Not Working | 103214555 | Electrical | PENDING
05.07.26 | 19 | FAE | Fae Gf Apple Atrium Esc Side Panel Cracked | 103214566 | Civil | CLOSED
05.07.26 | 20 | FAE | Fae 1St Floor Common Area Near Home Bakery Restaurant Boh Door Need Paint Touch Up | 103214599 | Civil | CLOSED
05.07.26 | 21 | FAE | Fae Gf Staff Mwr 03 Cubicle Water Shataff Pipe Leaking | 103214920 | Mechanical | CLOSED
05.07.26 | 22 | FAE | Fae 2Nd Floor Mlb Male Prayer Room Air Condition Is Not Warm Customer Complaining Please Check | 103215166 | Mechanical | CLOSED
06.07.26 | 1 | FAE | Fae, Sf Perfumery Area Near Jardin Shop Hanging Light Not Working | 103216092 | Electrical | PENDING
06.07.26 | 2 | FAE | Fae 1St Floor High-End Male Washroom Baby Changing Room Wooden Cabinet Hinge Need To Fix | 103218180 | Civil | CLOSED
06.07.26 | 3 | FAE | Ceiling Bulb Is Fused Washroom Corridor Gina Fwr Fae | 103217943 | Electrical | PENDING
06.07.26 | 4 | FAE | Fae Blvd Fwr Wall Picture Frame Has Chip |  | Civil | PENDING
06.07.26 | 5 | FAE | Fae Blvd Fwr #1 Washbasin Require Silicon |  | Mechanical | PENDING
06.07.26 | 6 | FAE | Fae Sf Fpr #1 Door Entrance Door Stopper Is Broken | 103226195 | Civil | CLOSED
06.07.26 | 7 | FAE | Fae Tf Fwr #4 Washbasin Cabinet Door Hinge | 103213951 | Civil | PENDING
06.07.26 | 8 | FAE | Fae Sf Fwr Hi Most Of Cubical Inside Tiles And Drainage Corner Was Chipped. |  | Civil | PENDING
06.07.26 | 9 | FAE | Fae Ff Lobby Pe No. 1 Sitting Area Have Glass Protection Damaged. |  | Civil | PENDING
06.07.26 | 10 | FAE | Fae Viplounge Mwr Requirements For Floor Grouting | 103249525 | Civil | PENDING
06.07.26 | 11 | FAE | Fae Sf Esc No. 12 Have Bollard Getting Loose. | 103249744 | Civil | CLOSED
06.07.26 | 12 | FAE | Fae Sf Esc No. 30 Have Bollard Getting Loose. | 103249745 | Civil | CLOSED
06.07.26 | 13 | FAE | Fae Mlb Fpyr Ceiling Emergency Light Glass Cover Broken. |  | Electrical | PENDING
06.07.26 | 14 | FAE | Fae Mlb Fpyr 2Nd Entrance Door Tiles Chipped |  | Civil | PENDING
06.07.26 | 15 | FAE | Fae Mb F Pyr 2Nd Entrance Inside Corner Carpet Was Chipped. |  | Civil | PENDING
06.07.26 | 16 | FAE | Fae Fpyr Entrance Door Inside Rusty Have. |  | Civil | PENDING
06.07.26 | 17 | FAE | Fae Sf Mlb Fpyr 2Nd Door Frame Paint Chipped. |  | Civil | PENDING
06.07.26 | 18 | FAE | Fae Sf Mlb Fpyr 2Nd Door Frame Paint Chipped. |  | Civil | PENDING
06.07.26 | 19 | FAE | Fae Fpyr 1St Door Inside Paint Chipped. |  | Civil | PENDING
06.07.26 | 20 | FAE | Fae Sf Highend Fwr Lhs# Cub No. 4 Handshattaf Control Water Small Dripping Was Requirements For Silicone. | 103250115 | Mechanical | PENDING
06.07.26 | 21 | FAE | Fae Sf Hi Fwr Corridor Floor Tile Water Seepage. | 103250116 | Mechanical | PENDING
06.07.26 | 22 | FAE | Fae Sf Highend Fwr Bcr No. 1 Grouting Requirements | 103250168 | Civil | PENDING
06.07.26 | 23 | FAE | Fae Sf Highend Fwr Bcr No. 1 Grouting Requirements |  | Civil | PENDING
06.07.26 | 24 | FAE | Fae Sf Hi Fwr Bcr No. 1 Door Tiles Chipped. | 103250195 | Civil | PENDING
06.07.26 | 25 | FAE | Fae Sf Mlb Fwr Pod Drainage Cover Need To Fix . | 103250564 | Mechanical | PENDING
06.07.26 | 26 | FAE | Fae Gf Staff Mwr All Cubicles Blocked Needs To Rectify | 103250294 | Mechanical | PENDING
06.07.26 | 27 | FAE | Fae Sf Mlb Fpyr Ablution Have No.4 Soap Bottle Fix Area Need To Remove The Glue Mark. |  | Civil | PENDING
06.07.26 | 28 | FAE | Fae 1F High End Mwr Rhs Cubicle No 1 Tissue Roll Holder Cover Needs To Fix Properly | 103251632 | Civil | CLOSED
06.07.26 | 29 | FAE | Esc 25 - Side Wall Stained Marks - Ff Fae | 103252144 | Civil | PENDING
06.07.26 | 30 | FAE | Fae, Sf Boh Near 02.M.25 Fire Extinguisher Door And Fram Both Side Need To Paint Touch Up | 103252672 | Civil | CLOSED
06.07.26 | 31 | FAE | Fae 2Nd Floor Mlb Male Prayer Room Inside Ac Is Very Warm Need To Rectify Customer Complaining Please Check Now | 103253949 | Mechanical | CLOSED
06.07.26 | 32 | FAE | Fae,Sf Mlb Prayer Room Abortion Area Top Ceiling Need Paint Required | 103254672 | Civil | PENDING
07.07.26 | 1 | FAE | Fae, Sf Infront Of Ten 11 Piller Need To Paint Touch Up | 103260368 | Civil | PENDING
07.07.26 | 2 | FAE | Fae, 4F Mwr Janitor Room Ceiling Cracked Need To Paint Touch Up | 103260839 | Civil | CLOSED
07.07.26 | 3 | FAE | Fae, 4F Mwr Urinal Area Need To Change Grouting | 103260940 | Mechanical | PENDING
07.07.26 | 4 | FAE | Fae, 4F Mwr Cubicle #5 Lhs Wall Skirting Need To Put Grouting | 103261022 | Civil | CLOSED
07.07.26 | 5 | FAE | Fae Ff He Mwr Chandeliers Need To Inspection For The Cleaning | 103262537 | Electrical | CLOSED
07.07.26 | 6 | FAE | Fae Ff High-End Fwr Pod Soap Sensor Is Not Working | 103262917 | Electrical | PENDING
07.07.26 | 7 | FAE | Fae Sf Mlb Corridor The Wooden Is Damage Need To Rectify Please | 103267733 | Civil | PENDING
07.07.26 | 8 | FAE | Fae Gf Tod'S Mwr Rhs 2Nd Cubicle Handshattaf Leakage Need To Rectify Please | 103276971 | Mechanical | CLOSED
07.07.26 | 9 | FAE | Fae Gf Gina Fwr Cubicle 3 The Door Is Very Difficult And Hard To Open | 103287183 | Civil | PENDING
07.07.26 | 10 | FAE | Fae, Gf Gina Male Baby Room Wash Basin Area Joint Grout Missing | 103288786 | Mechanical | PENDING
07.07.26 | 11 | FAE | Fae, Gf Near Alfardan Jewellery Shop Wall Joint Need To Re-Paint Pls | 103288787 | Civil | PENDING
07.07.26 | 12 | FAE | Fae, Gf Gina Mwr Corridor Ceiling Corner Damaged | 103292324 | Civil | PENDING
07.07.26 | 13 | FAE | Fae, Sf Mlb Corridor Infront Of Fpr Ceiling Water Leakage Need To Rectified Immediately Please | 103293888 | Mechanical | CLOSED
07.07.26 | 14 | FAE | Fae 1St Floor Staff Mwr 1No Washbasin Area Hand Soap Tap Loose Condition Need To Be Tight | 103293883 | Mechanical | CLOSED
07.07.26 | 15 | FAE | Fae, Rooftop Infront Of Se 05 Wall Damage Need To Rectified | 103295405 | Civil | PENDING
07.07.26 | 16 | FAE | Fae, Rooftop Infront Of Se 05 Wall Need To Paint Touch Up | 103295405 | Civil | PENDING
07.07.26 | 17 | FAE | Fae, Rooftop Infront Of Se 05 Wall Damage Need To Rectified | 103295405 | Civil | PENDING
08.07.26 | 1 | FAE | Fae Ff He Fwr Rhs 8No, Cubicle Door Tiles Damage | 103296169 | Civil | PENDING
08.07.26 | 2 | FAE | Fae Gf Vip Mwr Left Side 06 Cubicle Wc Remote Has No Power Supply | 103296171 | Electrical | CLOSED
08.07.26 | 3 | FAE | Fae, 4F Mwr Pod Door Farm Skirting Need To Fixed | 103296269 | Civil | PENDING
08.07.26 | 4 | FAE | Fae Ff High-End Fwr Lhs Washbasin #8 Down Side There Is Leakage | 103321106 | Mechanical | PENDING
08.07.26 | 5 | FAE | Fae Vip Lounge Infront Of Fwr Wall Painting Required Please | 103321201 | Civil | PENDING
08.07.26 | 6 | FAE | Fae Tf Fwr Washbasin Area #4 Cabinet Door Is Loss Needs To Fixed | 103322629 | Civil | PENDING
08.07.26 | 7 | FAE | Fae Gf Swr Female Washroom Wall Corner And Floor Required Grouting |  | Civil | PENDING
08.07.26 | 8 | FAE | Fae 2F Perfumery Area Srart From Enhance Shop Until Dior Shop 5 Light Busted |  | Electrical | PENDING
08.07.26 | 9 | FAE | Fae Sf Byriedo Shop And Chanel Shop Between Hanging Waill Light Getting Loose. |  | Electrical | PENDING
08.07.26 | 10 | FAE | Fae Sf Byredo Shop Front Of Ceiling Water Dripping. |  | Mechanical | PENDING
08.07.26 | 11 | FAE | Fae Sf Perfume Area Manish Malotra Shop Beside Fire Extinguisher Door Marble Crack. |  | Civil | PENDING
08.07.26 | 12 | FAE | Fae Sf Hi Fwr Corridor Tiles Seepage. |  | Mechanical | PENDING
08.07.26 | 13 | FAE | Fae, Gf Vip Mwr Lhs 2Nd Cubicle Wash Basin Marble Require Grout | 103325747 | Civil | PENDING
08.07.26 | 14 | FAE | Fae, Gf Vip Mwr Urinal Area Lhs 2Nd & 3Rd Urinal Bottom Grout Missing | 103325749 | Mechanical | PENDING
08.07.26 | 15 | FAE | Fae, Gf Vip Mwr Urinal Area Rhs 2Nd Urinal Bottom Grout Missing | 103325749 | Mechanical | PENDING
08.07.26 | 16 | FAE | Fae, Gf Vip Mwr Lhs 6Th Cubicle Entrance Skirting Is Detached | 103325828 | Civil | PENDING
08.07.26 | 17 | FAE | Fae Sf Highend Fwr Lhs# Cub No. 6 Door Deatch. | 103325845 | Civil | PENDING
08.07.26 | 18 | FAE | Fae Sf Rhs# Cub No. 2 Skirting Need To Fix. | 103325846 | Civil | PENDING
08.07.26 | 19 | FAE | Fae Sf Byriedo Shop And Chanel Shop Between Hanging Waill Light Getting Loose. | 103325919 | Electrical | PENDING
08.07.26 | 20 | FAE | Fae Sf Perfume Area Manish Malotra Shop Beside Fire Extinguisher Door Marble Crack. | 103325920 | Civil | PENDING
08.07.26 | 21 | FAE | Fae 2F Perfumery Area Srart From Enhance Shop Until Dior Shop 5 Light Busted | 103326265 | Electrical | PENDING
08.07.26 | 22 | FAE | Fae 3F Mwr Pod Cubicle Wall Mounted Bin Door Not Closing Properly | 103326362 | Civil | PENDING
08.07.26 | 23 | FAE | Fae Sf Hi Fwr Corridor Tiles Seepage. | 103326500 | Mechanical | PENDING
08.07.26 | 24 | FAE | Fae Sf Mlb 1 Slide Door Closing Time Sound Coming. | 103326850 | Civil | PENDING
08.07.26 | 25 | FAE | Fae Gf Fswr Washbasin No 3 Soap Sensor Is Not Working | 103329070 | Electrical | PENDING
08.07.26 | 26 | FAE | Fae Ff High End Fwr, Rhs Side 2No,Washbasin Cabinet Door Damage | 103298011 | Civil | PENDING
08.07.26 | 27 | FAE | Fae Basment Mwr Right 1St Cubicle Partition Wall Joint Ties Cracked | 103330264 | Civil | PENDING
08.07.26 | 28 | FAE | Fae, Sf Mlb Mpr Ac Is Not Colling Very Warm Need To Rectified Please | 103330315 | Mechanical | PENDING
08.07.26 | 29 | FAE | Fae, Tf Infront Of Esc-33&34 Near Marble Need To Put Grouting | 103330969 | Civil | PENDING
08.07.26 | 30 | FAE | Fae Basment Near Service Lift 3And 4 Door And Door Frame Painting Required Security Room | 103331041 | Civil | PENDING
08.07.26 | 31 | FAE | Fae Gf Vip Mwr Washbasin Area Water Tap Turner Is Loose Condition | 103330410 | Mechanical | PENDING
08.07.26 | 32 | FAE | Fae, Tf Mwr Cubicle #3/#4 Drainage Area Need To Put Grouting | 103331018 | Mechanical | PENDING
09.07.26 | 1 | FAE | Basement Boh Near Se-11 Wall Damage | 103333823 | Civil | PENDING
09.07.26 | 2 | FAE | Third Floor Mwr Lhs Washbasin #2 Soap Sensor Is Not Working | 103333890 | Electrical | CLOSED
09.07.26 | 3 | FAE | Basement Boh Near Se-11 Wall Need To Paint Touch Up | 103333853 | Civil | PENDING
09.07.26 | 4 | FAE | Vip Lounge Washroom Corridor Celling Access Panel Side Is Different Colour Need To Paint Same Colour | 103333906 | Civil | PENDING
09.07.26 | 5 | FAE | Gf Tods Fwr Lhs #6 Cubicle Wooden Wall Needs To Fixed Properly It Shaking |  | Civil | PENDING
09.07.26 | 6 | FAE | Gf Swr Female Last Cubicle Between Door Frame And Wall Required Grouting |  | Civil | PENDING
09.07.26 | 7 | FAE | Fourth Floor Fwr Pod Drainage Required Grouting | 103341470 | Mechanical | PENDING
09.07.26 | 8 | FAE | Sf High-End Fwr From Janitor Rhs #3 Cubicle Door Is Hard To Open And Close Needs To Fixed | 103341685 | Civil | PENDING
09.07.26 | 9 | FAE | Sf Mlb Mwr Cubicle #4 Wc Remote Not Working Need To Change Battery | 103335742 | Electrical | CLOSED
09.07.26 | 10 | FAE | Sf Esc-30 Seafty Bollard Lose Condition Need To Rectified | 103336058 | Civil | PENDING
09.07.26 | 11 | FAE | Sf High-End Fwr From Janitor Rhs 9 And 10 Door Frame Tile Needs To Fixed | 103341768 | Civil | PENDING
09.07.26 | 12 | FAE | Blvd Fwr Infront Cubicles Area #1,2 And 3 Washbasin Mirror Top Ceilings Requires Painting | 103342631 | Civil | PENDING
09.07.26 | 13 | FAE | Ff High-End Fwr Entrance Of The Washroom Lhs Marble Wall Tile Is Cracked |  | Civil | PENDING
09.07.26 | 14 | FAE | Basement Fwr Lhs #5 Washbasin Water Tap Sensor Is Not Working | 103353562 | Electrical | PENDING
09.07.26 | 15 | FAE | Sf Mlb Fwr Last Washbasin Water Tap Sensor Is Not Working |  | Electrical | PENDING
09.07.26 | 16 | FAE | Gf Gina Fwr From Pod Cubicle #4 Drainage Cement Cover Is Out Needs To Fixed |  | Mechanical | PENDING
09.07.26 | 17 | FAE | Fourth Floor Fwr Authorized Personnel Only Door It Damage And Door Frame Requires Grouting |  | Civil | PENDING
09.07.26 | 18 | FAE | Gf Gina Fwr From Pod Cubicles #4 Flash Bottom Is Out It Requires Silicon |  | Mechanical | PENDING
09.07.26 | 19 | FAE | Sf Hi Fwr Lhs# Cub No. 6 Door Frame Paint Chipped. |  | Civil | PENDING
09.07.26 | 20 | FAE | Third Floor Fl Fwr Vanity Counter Last Cabinet Door Hinge Almost Removed And Door Was Not Closed. |  | Civil | PENDING
09.07.26 | 21 | FAE | Viplounge Meeting Room Door Lock Discoloured. |  | Civil | PENDING
09.07.26 | 22 | FAE | Viplounge Spa Room Grouting Requirements |  | Civil | PENDING
09.07.26 | 23 | FAE | Viplounge Spa Room Ceiling Paint Was Discoloured. |  | Civil | PENDING
09.07.26 | 24 | FAE | Viplounge Fwr Wall Paint Need To Touch Up. |  | Civil | PENDING
09.07.26 | 25 | FAE | Viplounge Fwr Corridor Tiles Need To Touch Up. |  | Civil | PENDING
09.07.26 | 26 | FAE | Fourth Floor Fl Fwr Bcr No. 1 Door Frame Paint Chipped. |  | Civil | PENDING
09.07.26 | 27 | FAE | Third Floor Fl Fwr Bcr No. 2 Wall Grouting Requirements. |  | Civil | PENDING
09.07.26 | 28 | FAE | Sf Mlb Mwr Pod Cubicle Behind Wc Steel Came Out From Wall Need To Fix | 103367756 | Civil | PENDING
09.07.26 | 29 | FAE | Ff High-End Mwr Washbasin Area Below The Console Table Seitch Board Need To Fix | 103367785 | Electrical | CLOSED
09.07.26 | 30 | FAE | Ff Staff Mwr Washbasin No 4 Tap No Water Supply | 103367889 | Mechanical | CLOSED
09.07.26 | 31 | FAE | Fourth Floor Infront Of Blume Restaurant Ac Grill Water Dripping Need To Rectified Please | 103369317 | Mechanical | PENDING
09.07.26 | 32 | FAE | Vip Lounge Meeting Room Door Handles Lose Conditions Need To Rectified | 103369359 | Civil | PENDING
09.07.26 | 33 | FAE | Sf Boh Corridor Next To Sr-2Room 02.M.53 Minor Water Dripping Continuously From The Ceiling Access Panel | 103369404 | Mechanical | PENDING
10.07.26 | 1 | FAE | Gf Tods Corridor Wall Frame Picture In Front Of Tods Fwr Entrance Fell Off | 103370120 | Civil | PENDING
10.07.26 | 2 | FAE | 1St Floor Staff Mwr 4No Washbasin Area Hand Water Tap Sensor Is Not Working | 103370126 | Electrical | CLOSED
10.07.26 | 3 | FAE | 3Rd In Front Of Esc- 34 Top Cheling Ac Grill Area Paint Touch Up Required | 103375726 | Mechanical | PENDING
10.07.26 | 4 | FAE | Sf He Mwr Rhs 7Th Washbasin Cabinet Not Closing Properly Need To Be Rectify | 103375837 | Mechanical | PENDING
10.07.26 | 5 | FAE | Gf To Ff Esc 09 Side Panel Area Required Paint Touch Up | 103387340 | Civil | PENDING
10.07.26 | 6 | FAE | 2F Mlb Corridor Opposite P7 Glass Door Wall Discoloured Need Paint Touchup |  | Civil | PENDING
10.07.26 | 7 | FAE | 1F Infront Of Carpo Pillar Surroundings Chipped And Permanent Stain Need Paint Touchup | 103401552 | Civil | PENDING
10.07.26 | 8 | FAE | 1F Infront Of Voyage Restaurant Pillar Next To Plant Pot Has Chipped And Permanent Stain Need Paint Touchup | 103401475 | Civil | PENDING
10.07.26 | 9 | FAE | 4F Mwr Janitor Room Access Panel Water Leaking |  | Mechanical | PENDING
10.07.26 | 10 | FAE | 4F Mwr Janitor Room Access Panel Water Leaking |  | Mechanical | PENDING
10.07.26 | 11 | FAE | 3F Mwr Rhs Washbasin No 3 Soap Dispenser Sensor Not Working | 103401689 | Electrical | PENDING
10.07.26 | 12 | FAE | 4Th Fl Fwr Vanity Counter First One Up Ceiling Light Dim. |  | Electrical | PENDING
10.07.26 | 13 | FAE | Sf Mlb Fpyr Rhs# Ablution Beside Wall Skirting Cracked. | 103401446 | Mechanical | PENDING
10.07.26 | 14 | FAE | Sf Mlb Fpyr Rhs# Ablution Beside Wall Skirting Cracked. Proper To Fix Look Not Well. | 103401445 | Mechanical | PENDING
10.07.26 | 15 | FAE | Sf Mlb Fpyr Ablution Entry Wall Skirting Proper To Touch Up Looking Not Well | 103399042 | Mechanical | PENDING
10.07.26 | 16 | FAE | Gf Gina Mwr Rhs 3Rd Cubicle Skirting Is Loose | 103401773 | Civil | PENDING
10.07.26 | 17 | FAE | Vip Lounge Near Conferance Room Ceiling Need To Re-Paint | 103401772 | Civil | PENDING
10.07.26 | 18 | FAE | 1F Elevator Se 11 Boh Behind The Bin Permanent Stain Need Paint Touchup | 103402224 | Civil | PENDING
10.07.26 | 19 | FAE | 2F High-End Mwr Entrance Ceiling Light Needs To Change |  | Electrical | PENDING
10.07.26 | 20 | FAE | Vip Lounge Female Washroom Celling Access Panel Side Is Different Colour Need To Paint Same Colour | 103334051 | Civil | PENDING
10.07.26 | 21 | FAE | Fae Ff He Fwr Rhs 8No, Cubicle Wc Sid Cover Not To Be Fix Properly | 103405195 | Mechanical | PENDING
11.07.26 | 1 | FAE | Fae 4Th Floor Mwr The Recessed Door Handle Need To Rectify With Screw | 103410355 | Civil | PENDING
11.07.26 | 2 | FAE | Fae Sf Mlb Mwr Rhs 2Nd Cubicle Wc Remote Seat Cover Bottom Not Working Need To Rectif | 103410594 | Mechanical | PENDING
11.07.26 | 3 | FAE | Fae 4F Fwr #1 Bcr Water Dispenser Is Not Working |  | Mechanical | PENDING
11.07.26 | 4 | FAE | Fae Ff Infront Of Pe-08/09 Wall Painting Required Please | 103415826 | Civil | PENDING
11.07.26 | 5 | FAE | Fae 1F High-End Mwr Rhs Washbasin No 4 No Water Supply | 103432866 | Mechanical | CLOSED
11.07.26 | 6 | FAE | Fae Sf Mlb Cub No. 1 Grouting Requirements |  | Civil | PENDING
11.07.26 | 7 | FAE | Fae / Sf Mlb Fwr Cub No. 3 Wall Grouting Requirements |  | Civil | PENDING
11.07.26 | 8 | FAE | Fae Vip Lounge Boh Water Dripping From Ac Duct Need Assistance | 103432356 | Mechanical | PENDING
11.07.26 | 9 | FAE | Fae Viplounge Meeting Room Entrance Door Skirting Need To Touch Up. | 103432867 | Civil | PENDING
11.07.26 | 10 | FAE | Fae Viplounge Vip Meeting Room Wall Paint Yellow Stain Need To Touch Up. | 103432893 | Civil | PENDING
11.07.26 | 11 | FAE | Fae Viplounge Spa Room Door Grouting Requirements. | 103432895 | Civil | PENDING
11.07.26 | 12 | FAE | Fae / Sf Mlb Fwr Cub No. 3 Wall Grouting Requirements | 103432926 | Civil | PENDING
11.07.26 | 13 | FAE | Fae / Sf Mlb Fwr Janitor Room Door Closing Noisy Sound | 103432928 | Mechanical | PENDING
11.07.26 | 14 | FAE | Fae, Basement Mwr Rhs 6Th Cubicle Roll Tissue Dispenser Cover Detached | 103433377 | Civil | PENDING
11.07.26 | 15 | FAE | Fae 4F Fwr #1 Bcr Water Dispenser Is Not Working |  | Mechanical | PENDING
12.07.26 | 1 | FAE | Fae Ff High-End Fwr Rhs #2 Cabinet Door Hinges Detached And The Door Not Closing Properly | 103454550 | Civil | PENDING
12.07.26 | 2 | FAE | Fae Ff Hi Fwr Corridor Most Of Drainage Corner Was Chipped. Need To Fix |  | Mechanical | PENDING
12.07.26 | 3 | FAE | Fae Viplounge Meeting Room Door Back Side Wall Yellow Stain Mark.. |  | Civil | PENDING
12.07.26 | 4 | FAE | Fae Ff Hi Fwr Corridor Most Of Drainage Corner Was Chipped. Need To Fix | 103470482 | Mechanical | PENDING
12.07.26 | 5 | FAE | Fae Viplounge Meeting Room Ceiling Gap Have Need To Touch Up Still Not Rectify Yet. |  | Civil | PENDING
12.07.26 | 6 | FAE | Fae Sf Rhs# Wb# No.2 Tap Not Working. | 103472600 | Mechanical | PENDING
12.07.26 | 7 | FAE | Fae, Staircase 49A Wall Paint Is Damaged | 103472324 | Civil | PENDING
12.07.26 | 8 | FAE | Fae Gf Gina Fwr 1St Bcr Behind Glass Door Frame Chipped | 103472504 | Civil | PENDING
12.07.26 | 9 | FAE | Fae Sf Hi Fwr Lhs # Cub No .4 Door Stopper Getting Loose. | 103472891 | Civil | PENDING
12.07.26 | 10 | FAE | Fae, Gf Gina Mwr Pod Cubicle Water Tap Is Leaking | 103472739 | Mechanical | PENDING
12.07.26 | 11 | FAE | Fae, Blvd Mwr Opposite Janitor Room Cubicle Door Frame Chipped | 103472765 | Civil | PENDING
12.07.26 | 12 | FAE | Fae, Gf Vip Mwr Lhs 5Th Cubicle Wc Remote Not Working For Lifting Seat Cover | 103472869 | Electrical | PENDING
12.07.26 | 13 | FAE | Fae Mlb Fwr Wb# No. 3 Tap Water Not Coming | 103476254 | Mechanical | CLOSED
12.07.26 | 14 | FAE | Fae 2F High-End Mwr Lhs Washbasin No 2 Tap Loose Need To Fix | 103476283 | Mechanical | PENDING
12.07.26 | 15 | FAE | Fae 1St Floor Boh P4 Staircase No 36 Door Entrance Need To Paint Required | 103478297 | Civil | PENDING
12.07.26 | 16 | FAE | Fae Vip Lounge Female Washroom Floor Tiles Damage Need To Fix | 103478425 | Civil | PENDING
12.07.26 | 17 | FAE | Fae, 4F Mwr Hk Janitor Room Ceiling Access Panel Cracked Need To Paint Touch Up | 103478864 | Civil | CLOSED
12.07.26 | 18 | FAE | Fae 1St Floor Staff Mwr Main Door Need To Paint Touch | 103479309 | Civil | CLOSED
12.07.26 | 19 | FAE | Fae Basment Mwr Right 06 Cubicle Roll Tissue Dispenser Screw Damaged | 103479387 | Civil | CLOSED
12.07.26 | 20 | FAE | Fae, 4F Mwr Pod Door Farm Chipped Need To Fixed | 103479355 | Civil | PENDING
12.07.26 | 21 | FAE | Fae, 4F Mwr Pod Door Farm Skirting Need To Put Grouting | 103479355 | Civil | PENDING
12.07.26 | 22 | FAE | Fae 1St Floor Boh Near Service Lift Se 04 Landing Area Boh Door Need Paint Touch Up | 103480088 | Civil | PENDING
13.07.26 | 1 | FAE | Fae Gf High Fashion Celling Light Need To Clean As Per Sfm | 103481655 | Electrical | PENDING
13.07.26 | 2 | FAE | Fae Vip Lounge Boh Ac Vent To Minor Water Dripping On Going Continuously | 103481703 | Mechanical | PENDING
13.07.26 | 3 | FAE | Fae Gf Gina Mwr Pod Cubicle Handshattaf Leakage Need To Rectify Please | 103470910 | Mechanical | CLOSED
13.07.26 | 4 | FAE | Fae Tf Fwr #1 Cubicle Hand Shattaf Is Broken |  | Mechanical | CLOSED
13.07.26 | 5 | FAE | Fae Gf Tods Mwr Cubicle Number 5: The Left Side Seat Cover Botton Is Not Functioning | 103498720 | Civil | PENDING
13.07.26 | 6 | FAE | Fae Sf Mlb Fpyr Ablution Small Side Wall Tile Need To Fix. |  | Mechanical | CLOSED
13.07.26 | 7 | FAE | Fae Sf Mlb Fpyr Ablution Area Grouting Requirements. |  | Mechanical | CLOSED
13.07.26 | 8 | FAE | Fae Sf Mlb Fpyr Ablution Have No. 1 Glass Stand Handsoap Need To Fix . |  | Mechanical | PENDING
13.07.26 | 9 | FAE | Fae Sf Mlb Fpyr Ablution Small Side Have Wall Glass Was Black Stain Mark. | 103505177 | Mechanical | PENDING
13.07.26 | 10 | FAE | Fae Sf Mlb Fpyr Ablution Small Side Grill Was Dent Need To Fix Proper . | 103505225 | Mechanical | PENDING
13.07.26 | 11 | FAE | Fae Sf Mlb Fpyr Door Inside Light Most Of Wood Frame Chipped Need To Fix | 103505128 | Electrical | PENDING
13.07.26 | 12 | FAE | Fae Gf Near Tod'S Mwr Boh Door Very Noisy Need To Rectify Please | 103500611 | Mechanical | PENDING
13.07.26 | 13 | FAE | Fae 4Th Fwr Bcr No.1 Water Dispenser Was Erra Still Not Rectify Yet. |  | Mechanical | PENDING
13.07.26 | 14 | FAE | Fae 4Th Fwr Pod Skirting Grouting Requirements | 103513419 | Civil | PENDING
13.07.26 | 15 | FAE | Fae Ff Hi Fwr Lhs# Cub No. 2 Handshattaf Holder Getting Loose. | 103513354 | Mechanical | PENDING
13.07.26 | 16 | FAE | Fae 1F Apple Atrium Next To Marella Shop Light Wire Visible Need To Fix Properly | 103513423 | Electrical | PENDING
13.07.26 | 17 | FAE | Fae Ff Highend Fwr Most Of Cub Have Wc Steel Hinges Was Discoloured. | 103513935 | Mechanical | PENDING
13.07.26 | 18 | FAE | Fae, Sf Mlb Mpr Inside Rhs Floor Light Not Working | 103516217 | Electrical | CLOSED
13.07.26 | 19 | FAE | Fae Gf Staff Mwr Washbasin 2Nd Water Tap Loose Condition | 103516258 | Mechanical | CLOSED
13.07.26 | 20 | FAE | Fae, 4F Infront Of Blume Restaurant Ceiling Near Ac Grill Water Dripping Need To Rectified Please | 103516265 | Mechanical | PENDING
13.07.26 | 21 | FAE | Fae 1St Floor Near P4 Boh Ceiling Light Is Not Working | 103516273 | Electrical | CLOSED
13.07.26 | 22 | FAE | Fae, Tf Lift Lobby Infront Of Pe 06 Ac Grill Water Dripping Need To Rectified Please | 103516336 | Mechanical | PENDING
13.07.26 | 23 | FAE | Fae, Sf Boh Near Origami Wall Need To Paint Touch Up | 103517388 | Civil | CLOSED
13.07.26 | 24 | FAE | Fae, Sf He Mwr Bcr Water Dispenser Icon Not Working Need To Rectified Please | 103517517 | Mechanical | CLOSED
13.07.26 | 25 | FAE | Fae Basment Mwr Jainator Room Door Handle Need To Fix | 103517999 | Civil | CLOSED
13.07.26 | 26 | FAE | Fae 1St Floor Common Area P5 Welcome Lobby Ac Grill To Minor Water Dripping Continously | 103518047 | Mechanical | CLOSED
13.07.26 | 27 | FAE | Ceiling Around Bulb 💡 Need Touch Last Cubicle Blovd Fwr | 103518837 | Electrical | CLOSED
14.07.26 | 1 | FAE | 4F Mwr Hk Janitor Room Ceiling Access Panel Cracked And Near Light Water Mark Need To Paint Touch Up | 103522945 | Electrical | PENDING
14.07.26 | 2 | FAE | Sf Mlb Mwr Cubicle #1 Pipe Holder Need To Change | 103522967 | Mechanical | PENDING
14.07.26 | 3 | FAE | Gf Tod'S Mwr Lhs 5Th Cubicle Wc Remote Seat Cover Bottom Not Working Need To Rectify | 103524899 | Mechanical | PENDING
14.07.26 | 4 | FAE | Gf Tod'S Mwr Lhs 4Th Cubicle Wc Remote Flash Bottom Not Working Need To Rectify | 103524943 | Mechanical | PENDING
14.07.26 | 5 | FAE | Sf Mlb Mwr Floor Grouting Required Please | 103530972 | Civil | PENDING
14.07.26 | 6 | FAE | GF Gina Fwr From Pod Cubicle #5 Flash Bottom Is Out Needs To Fixed | 103535199 | Civil | PENDING
14.07.26 | 7 | FAE | SF He Mwr Wc Seat Cover Steel Colour Faded | 103535124 | Mechanical | PENDING
14.07.26 | 8 | FAE | FAE GF Gina Fwr 2Nd Bcr Behind Door Frame Chipped | 103541956 | Civil | PENDING
14.07.26 | 9 | FAE | GF Vip Mwr Lhs 5Th Cubical Wc Seat Cover Not Working | 103541908 | Mechanical | PENDING
14.07.26 | 10 | FAE | GF Balconi Side Sr-8 Room, Gl.M.57 Floor Need To Re-Paint | 103542265 | Civil | PENDING
14.07.26 | 11 | FAE | GF Near Piaget Shop Escalator Safety Bollards Loose Condition | 103542246 | Civil | PENDING
14.07.26 | 12 | FAE | Fourth Floor Floor Mwr Underneath Cabinet Water Linking From The Grouting Required To Fix On The Rightside | 103555245 | Mechanical | PENDING
14.07.26 | 13 | FAE | FAE GF Near Bvlgari Boh Door Is Not Closing Automatically | 103555948 | Civil | PENDING
14.07.26 | 14 | FAE | FAE GF Vip Mwr Jainator Room Washbasin Water Tap Leaking | 103555928 | Mechanical | PENDING
14.07.26 | 15 | FAE | FF High-End Mwr Rhs 5No Washbasin Area Hand Soap Sensor Not Working | 103556812 | Electrical | PENDING
14.07.26 | 16 | FAE | Third Floor Mwr Rhs Washbasin Mountain Bin Need To Put Silicon | 103557094 | Mechanical | PENDING
14.07.26 | 17 | FAE | FF High Fashion Boh Door Need Paint Touch Up | 103557161 | Civil | PENDING
14.07.26 | 18 | FAE | Basement Level Boh Lift Se 07 & 08 Near Security Room Outside Ceiling To Waterleakage On Going Please Attend | 103557879 | Mechanical | PENDING
15.07.26 | 1 | FAE | SF MLB male prayer room inside every day 8 pm air condition getting very warm & hot customer complaining daily basis so AS PER your EFS team instruction can you send air condition Supervisor ,tonight for AC servicing tonight | 103558106 | Mechanical | PENDING
15.07.26 | 2 | FAE | BLVD mwr 1st cubicle wc remote has no power supply | 103561232 | Electrical | PENDING
15.07.26 | 3 | FAE | FF HIGH-End MWR RHS 2NO washbasin down cabinet inside faded need to paint required | 103561920 | Mechanical | PENDING
15.07.26 | 4 | FAE | FF HIGH-End MWR LHS 1no washbasin area under down cabinet inside the soap sensor pipe leakage need to fix properly tonight | 103561936 | Electrical | PENDING
15.07.26 | 5 | FAE | FF high-end FWR #4 cubicle RHS flush bottom required silicon | 103571877 | Mechanical | PENDING
15.07.26 | 6 | FAE | FF high-end FWR markup area drainage needs to fixed properly the cover is not equal with with the drainage gap | 103571893 | Mechanical | PENDING
15.07.26 | 7 | FAE | Third Floor FWR washbasin area inside cabinet where they place the bin the wooden floors it damage | 103574131 | Mechanical | PENDING
15.07.26 | 8 | FAE | FF HE MWR Side BOH Door handle not working need to rectify please | 103576003 | Civil | PENDING
15.07.26 | 9 | FAE | FF HE MWR Side BOH Door handle not working need to rectify please | 103576637 | Civil | PENDING
15.07.26 | 10 | FAE | 3rd FL Fwr Vanity inside Wood was damaged. |  | Civil | PENDING
15.07.26 | 11 | FAE | Third Floor FL Fwr Vanity Counter last Cabinet doornot proper to close. |  | Civil | PENDING
15.07.26 | 12 | FAE | FAE 3rd FL Fwr Corridor Skirting Tiles Grouting have Near by Cubical no. 3 |  | Civil | PENDING
15.07.26 | 13 | FAE | SF MLB Fwr Corridor Wall Tiles cracked near by Cub no. 1 | 103587630 | Civil | PENDING
15.07.26 | 14 | FAE | SF MLB fwr Most of Cub have Handshattaf Holder Discoloured. | 103587632 | Mechanical | PENDING
15.07.26 | 15 | FAE | Third Floor Fl Fwr Cub no.1 Floor Tiles Minor Cracked. | 103587673 | Civil | PENDING
15.07.26 | 16 | FAE | SF ML B FPYR Ablution Area No. 1 Handsoap Glass Stand getting Loose need to fix . | 103586773 | Mechanical | PENDING
15.07.26 | 17 | FAE | FF boh beside Female staff washroom opposite to SR -3 Room 01.M.54 wall seepage | 103586882 | Mechanical | PENDING
15.07.26 | 18 | FAE | Third Floor mwr BCR above baby bed light needs to switched off | 103587631 | Electrical | PENDING
15.07.26 | 19 | FAE | SF MLB MPR Ablution area tap No 1 screw missing | 103587638 | Mechanical | PENDING
15.07.26 | 20 | FAE | FF FL Blume Shop Front of Ceiling Minor water dripping. | 103586986 | Mechanical | PENDING
15.07.26 | 21 | FAE | SF Highend Lobby PE .06 Elevator Up AC Minor Water Dripping. | 103587703 | Mechanical | PENDING
15.07.26 | 22 | FAE | BV near service lift 1&2 boh water leaking from celling | 103592727 | Mechanical | PENDING
15.07.26 | 23 | FAE | SF MLB MPR AC is not colling very warm need to rectified please customer complaining | 103596666 | Mechanical | PENDING
16.07.26 | 1 | FAE | Staircase no 36 level 10 wall need to paint touch up | 103599605 | Civil | PENDING
16.07.26 | 2 | FAE | GF Tod'S Mwr Lhs 6Th Cubicle Washbasin Silicon Required Please | 103603324 | Mechanical | PENDING
16.07.26 | 3 | FAE | FF high-end FWR #3 cubicle RHS door lock is loss |  | Civil | PENDING
16.07.26 | 4 | FAE | SF MLB Fwr POD have wall mount bin Lock need to change Bcoz not open. |  | Civil | PENDING
16.07.26 | 5 | FAE | SF P8 seating area 2 wall cracked need paint touchup | 103620870 | Civil | PENDING
16.07.26 | 6 | FAE | SF P8 seating area 1 wall discolored and chipped need paint touchup | 103620870 | Civil | PENDING
16.07.26 | 7 | FAE | FAE / FF Highend Fwr WB# No. 6 Tap not water Supply. |  | Mechanical | PENDING
16.07.26 | 8 | FAE | Fourth Floor Fwr Cub front Wall grouting requirements |  | Civil | PENDING
16.07.26 | 9 | FAE | FAE Viplounge Fwr Cub no. 1 Door frame Chipped. |  | Civil | PENDING
16.07.26 | 10 | FAE | GF vip mwr LHS 7th cubicle water tap knob cover not fixed | 103623593 | Mechanical | PENDING
16.07.26 | 11 | FAE | GF vip washroom corridor boh door not closed automaticaly | 103623577 | Civil | PENDING
16.07.26 | 12 | FAE | SF high-end mwr corridor ceiling needs a paint touch | 103624679 | Civil | PENDING
16.07.26 | 13 | FAE | FF high-end mwr LHS washbasin No 1 wooden cupboard hinghes needs to fix | 103624685 | Mechanical | PENDING
16.07.26 | 14 | FAE | FF near Novikov restaurant pillar permanent stain and mark need paint touchup | 103625040 | Civil | PENDING
16.07.26 | 15 | FAE | GF staff washroom boh entrance door not auto closed | 103625216 | Civil | PENDING
16.07.26 | 16 | FAE | Fourth Floor Fwr Cub front Wall grouting requirements | 103625145 | Civil | PENDING
16.07.26 | 17 | FAE | 1st floor staff washroom near two bistro restaurant boh door Need to paint required | 103629255 | Civil | PENDING
16.07.26 | 18 | FAE | 1st floor common area near two bistro restaurant boh on the floor crecked line need to fix | 103629255 | Civil | PENDING
16.07.26 | 19 | FAE | BOH lift SE 07 & 08 LG level boh wall side need to paint required | 103631163 | Civil | PENDING
16.07.26 | 20 | FAE | GF TODS MWR cubicle number 2 on the Left side WC has no power supply please assist us to rectify this issue | 103632515 | Electrical | PENDING
16.07.26 | 21 | FAE | SF Near SE-07&08 LHS 02.M.29 both door Need paint touch up | 103634395 | Civil | PENDING
16.07.26 | 22 | FAE | SF perfumery area infront of Hermes pillar need to paint touch up | 103634469 | Civil | PENDING
16.07.26 | 23 | FAE | SF Near Hermes BOH RHS door Need paint touch up | 103634470 | Civil | PENDING
16.07.26 | 24 | FAE | SF MLB corridor near FPR ceiling ac grill cracked need to paint touch up | 103634494 | Mechanical | PENDING
17.07.26 | 1 | FAE | Fourth Floor MWR RHS washbasin cabinet door not closing properly need to rectified | 103634720 | Mechanical | PENDING
17.07.26 | 2 | FAE | SF MLB mwr RHS 2nd cubicle WC remote is not working need to be rectify | 103637566 | Mechanical | PENDING
17.07.26 | 3 | FAE | FF HE MWR LHS 4th washbasin underneath pipe is damage need to be rectified | 103636608 | Mechanical | PENDING
17.07.26 | 4 | FAE | SF MLB MPR infront entrance door Need to paint touch up | 103637695 | Civil | PENDING
17.07.26 | 5 | FAE | SF MLB MPR inside floor light is not working | 103638121 | Electrical | PENDING
17.07.26 | 6 | FAE | Third Floor FWR washbasin area # 3 and 4 cabinet door is loss needs to fixed |  | Mechanical | PENDING
17.07.26 | 7 | FAE | SF MLB FWR last cubicle down side it cracked needs to fixed |  | Civil | PENDING
17.07.26 | 8 | FAE | SF MLB FWR all WCS behind seat cover required silicon |  | Mechanical | PENDING
17.07.26 | 9 | FAE | SF MLB FWr AC paint Requirements |  | Mechanical | PENDING
17.07.26 | 10 | FAE | SF MLB FPYR Small Ablution Area RHS# Wall Steel Skirting need to fix. | 103657167 | Mechanical | PENDING
17.07.26 | 11 | FAE | SF MLB FWr AC paint Requirements . | 103657369 | Mechanical | PENDING
17.07.26 | 12 | FAE | SF MLB Fwr Last Cubicle have Skirting need to touch up. | 103657190 | Civil | PENDING
17.07.26 | 13 | FAE | Viplounge Fwr Cub no. 1 Door frame Chipped. | 103621167 | Civil | PENDING
17.07.26 | 14 | FAE | SF MLB Fwr POD have wall mount bin Lock need to change Bcoz not open. | 103621375 | Civil | PENDING
17.07.26 | 15 | FAE | First Floor welcome court parking signage font lights are not working | 103659377 | Electrical | PENDING
17.07.26 | 16 | FAE | Second Floor perfumery area infront of DOLCE AND GABBANA carpet electric cable socket needs to fix | 103666754 | Electrical | PENDING
17.07.26 | 17 | FAE | SF mlb MPR lights are not functioning | 103666250 | Electrical | PENDING
17.07.26 | 18 | FAE | Second Floor MLB MWR cubicle number 2 remote not working | 103666953 | Electrical | PENDING
17.07.26 | 19 | FAE | Second floor HIGH-End MWR LHS 4no cubicle inside the door stopper rubber need to fix | 103666950 | Civil | PENDING
17.07.26 | 20 | FAE | First floor HIGH-End female washroom outside wall wooden cabinet inside the light is not working | 103667493 | Electrical | PENDING
17.07.26 | 21 | FAE | Third Floor AC vent ceiling access panel requires painting in front of GRAN COFFEE ceiling | 103669608 | Mechanical | PENDING
17.07.26 | 22 | FAE | SF BOH next to Manish maihotra shop water dripping continuously from the ceiling access panel | 103669649 | Mechanical | PENDING
17.07.26 | 23 | FAE | First floor staff female washroom outside on the floor crecked need to fix | 103669787 | Civil | PENDING
18.07.26 | 1 | FAE | GF star atrium GSD DOOR is not closing coz magnetic is loose condition | 103671504 | Civil | PENDING
18.07.26 | 2 | FAE | SF MLB FWR #2 cubicle WC seat cover is not opening by remote or manually needs to fixed @EFS Helpdesk | 103687024 | Mechanical | PENDING
18.07.26 | 3 | FAE | SF FPR first door entrance near green sofa marble tile is broken needs to fixed |  | Civil | PENDING
18.07.26 | 4 | FAE | GF Gina FWR from pod cubicle #5 flush bottom is out needs to fixed |  | Mechanical | PENDING
18.07.26 | 5 | FAE | GF vip mwr LHS 4th cubicle wash basin silicone gap need to fill | 103693880 | Mechanical | PENDING
18.07.26 | 6 | FAE | GF vip mwr RHS 4th cubicle wash basin silicone gap need to fill | 103693880 | Mechanical | PENDING
18.07.26 | 7 | FAE | GF vip mwr dressing area wooden surface chipped | 103693889 | Civil | PENDING
18.07.26 | 8 | FAE | FF Highend fwr Entrance Ceiling light Blinking. | 103700665 | Electrical | PENDING
18.07.26 | 9 | FAE | FF Highend fwr BCR No. 2 Ceiling light Blinking. | 103700667 | Electrical | PENDING
18.07.26 | 10 | FAE | Third Floormwr BCR above baby bed light surrounding cracked | 103700692 | Electrical | PENDING
18.07.26 | 11 | FAE | Fourth Floor near BLUME resturent escalator bollard losse condition | 103700781 | Civil | PENDING
18.07.26 | 12 | FAE | First Floor high-end washrooms corridor infront of fwr light busted |  | Electrical | PENDING
18.07.26 | 13 | FAE | First Floor high-end washrooms corridor infront of fwr 2 wooden inside lights are busted |  | Electrical | PENDING
18.07.26 | 14 | FAE | Third Floor MWR RHS cubicle side washbasin near skirting water coming need to rectified | 103703724 | Mechanical | PENDING
18.07.26 | 15 | FAE | SF P8 lobby entrance door Need to paint touch up | 103704520 | Civil | PENDING
18.07.26 | 16 | FAE | Fourth Floor BOH rooftop near SE-11 RHS wall need to paint touch up | 103704559 | Civil | PENDING
18.07.26 | 17 | FAE | Third Floor near Gran caffe BOH LHS wall need to paint touch up | 103704798 | Civil | PENDING
18.07.26 | 18 | FAE | Third Floor near Gran caffe BOH LHS wall need to paint touch up | 103704830 | Civil | PENDING
19.07.26 | 1 | FAE | SF Near HE WR corridor LHS BOH wall need to paint touch up | 103707661 | Civil | PENDING
19.07.26 | 2 | FAE | Fourth Floor POD inside open button need to fixed | 103707693 | Civil | PENDING
19.07.26 | 3 | FAE | First floor HIGH-End MWR LHS 1no washbasin wooden cabinet hinge broken need to fix | 103707749 | Mechanical | PENDING
19.07.26 | 4 | FAE | First floor HIGH-End MWR RHS 4no cubicle outside skirting cracked need to fix | 103707751 | Civil | PENDING
19.07.26 | 5 | FAE | First floor HIGH-End MWR LHS 1NO WASHBASIN AREA BIN AROUND NEED TO PUT SILICONE | 103707966 | Mechanical | PENDING
19.07.26 | 6 | FAE | SF HE MWR LHS cubicle no #2 WC REMOTE need to change battery is not working | 103707960 | Electrical | PENDING
19.07.26 | 7 | FAE | GF near burma floor socket cover steel come out need to fix immediately HAZARD | 103708707 | Electrical | PENDING
19.07.26 | 8 | FAE | Cover steel kept in near Jimmy choo fire extinguisher cabinet in side |  | Civil | PENDING
19.07.26 | 9 | FAE | Fourth Floor MWR near urinal door Need paint touch up | 103719468 | Mechanical | PENDING
19.07.26 | 10 | FAE | SF Near HE WR LHS BOH Door touch the wall and wall got damage need to rectified | 103720642 | Civil | PENDING
19.07.26 | 11 | FAE | FAE INFRONT OF SF MLB FWR WATER LEAKAGE NEED TO RECTIFY PLEASE | 103731759 | Mechanical | PENDING
19.07.26 | 12 | FAE | FAE FF Highend fwr RHS# Cub no.2 Door Frame paint Chipped. |  | Civil | PENDING
19.07.26 | 13 | FAE | FAE FF Hi Fwr RHS# Cub no.4 Vanity Cover need to fix |  | Civil | PENDING
19.07.26 | 14 | FAE | FAE FF Hi fwr RHS# Cub no.2 Skirting Cracked. |  | Civil | PENDING
19.07.26 | 15 | FAE | Third Floor FL fwr WB # Silicone Requirements |  | Mechanical | PENDING
19.07.26 | 16 | FAE | First Floor elevators PE 08,09, beside wall has hole | 103737384 | Civil | PENDING
19.07.26 | 17 | FAE | First Floor high-end mwr LHS washbasin No 1 wooden cupboard hinghes needs to fix | 103737468 | Mechanical | PENDING
19.07.26 | 18 | FAE | GF vip mwr LHS 6th cubicle door frame is chipped | 103738123 | Civil | PENDING
19.07.26 | 19 | FAE | GF vip mwr RHS 2nd cubicle wash basin silicone gap need to fill | 103738096 | Mechanical | PENDING
19.07.26 | 20 | FAE | FAE, Blvd mwr RHS 2nd cubicle wash basin water tap loose condition | 103740171 | Mechanical | PENDING
19.07.26 | 21 | FAE | FAE 1st floor HIGH-End MWR baby changing room main door skirting wall paper detached need to fix | 103740393 | Civil | PENDING
19.07.26 | 22 | FAE | FAE, SF BOH infront staircase 04c water leakage NEED TO rectified please | 103740421 | Mechanical | PENDING
19.07.26 | 23 | FAE | FAE vip lounge entrance RHS shutter door gap steel detached need to fix with glue | 103740737 | Civil | PENDING
19.07.26 | 24 | FAE | FAE 1st floor common area apple store white color planter light is not working | 103740787 | Electrical | PENDING
19.07.26 | 25 | FAE | FAE 1st floor HIGH-End MWR LHS 8 no cubicle outside skirting wall paper detached need to fix | 103741469 | Civil | PENDING
19.07.26 | 26 | FAE | SF infront Novikov ceiling water marks need to paint touch up | 103743116 | Mechanical | PENDING
20.07.26 | 1 | FAE | First floor staff mwr ceiling ac vent different color need to paint same color | 103743741 | Mechanical | PENDING
20.07.26 | 2 | FAE | SF Transguard store room inside ceiling water mark need to paint touch up | 103744782 | Mechanical | PENDING
20.07.26 | 3 | FAE | SF HE MWR washbasin corner both side Silicon required | 103747301 | Mechanical | PENDING
20.07.26 | 4 | FAE | GF P3 VALET LOUNGE WATER LEAKAGE FROM THE CEILING NEED TO RECTIFY | 103756236 | Mechanical | PENDING
20.07.26 | 5 | FAE | GF P3 Valet lounge ceiling paint damaged need to repaint please | 103765023 | Civil | PENDING
20.07.26 | 6 | FAE | SF Infront Of PE-05/06 Wooden colour faded repaint required please | 103765955 | Civil | PENDING
20.07.26 | 7 | FAE | GF TODS MWR cubicle number 6 on the Left side door frame edges chipped | 103708145 | Civil | PENDING
20.07.26 | 8 | FAE | GF Valet lounge ceiling has peeled off and there's water dripping continuously from the ceiling joints | 103765842 | Mechanical | PENDING
20.07.26 | 9 | FAE | GF TODS MWR cubicle number 2 on the Left side WC seat cover not functioning properly | 103768191 | Mechanical | PENDING
20.07.26 | 10 | FAE | GF TODS MWR cubicle number 4 door not closing properly | 103768083 | Civil | PENDING
20.07.26 | 11 | FAE | BLVD Prasad sides carpet need to fix at the corner on the right side | 103768604 | Civil | PENDING
20.07.26 | 12 | FAE | FAE FF Highend fwr LHS# Cub 5 Handshattaf holder getting loose. | 103768367 | Mechanical | PENDING
20.07.26 | 13 | FAE | 2F perfumery area start from medi clinic until dior shop 5 lights are busted | 103773834 | Electrical | PENDING
20.07.26 | 14 | FAE | FAE FF Hi fwr LHs# Cub no. 5 Remote have Flush Function not working. | 103773911 | Mechanical | PENDING
20.07.26 | 15 | FAE | Third Floor Fwr Cub no. 2 WC Behind Grouting requirements. |  | Mechanical | PENDING
20.07.26 | 16 | FAE | Third Floor Fwr Pod Skirting need to fix | 103774953 | Civil | PENDING
20.07.26 | 17 | FAE | GF Gina MWR cubicle number 2 from the POD flush botton is damaged needs to fix | 103776094 | Mechanical | PENDING
20.07.26 | 18 | FAE | SF MLB MWR Cubicle #5 WC remote not working need to change battery | 103776324 | Electrical | PENDING
20.07.26 | 19 | FAE | FAE BV near public elevator 5 and 6 boh celling access panel damaged and also painting required | 103776325 | Civil | PENDING
20.07.26 | 20 | FAE | FAE GF comman area near trove restaurant celling ac vent side painting required | 103776327 | Mechanical | PENDING
20.07.26 | 21 | FAE | FAE GF near gia sitting area celling cracked | 103776330 | Civil | PENDING
20.07.26 | 22 | FAE | Fourth Floor MWR cubicle #2 door frame skirting need to fixed | 103776487 | Civil | PENDING
20.07.26 | 23 | FAE | Fourth Floor MWR cubicle #5 door farm skirting need to fixed | 103776487 | Civil | PENDING
20.07.26 | 24 | FAE | Fourth Floor MWR POD Door Open button need to fix and put silicon | 103776488 | Mechanical | PENDING
20.07.26 | 25 | FAE | FAE basment mwr washbasin all sink new silicone required | 103776717 | Mechanical | PENDING
20.07.26 | 26 | FAE | SF MLB corridor infront of FPR ceiling access panel cracked and water mark need to paint touch up | 103776784 | Mechanical | PENDING
20.07.26 | 27 | FAE | 1st floor staff MWR maindoor corner need to paint required | 103776814 | Civil | PENDING
20.07.26 | 28 | FAE | SF Near Hermes BOH LHS 02.M.44 door Need paint touch up | 103777041 | Civil | PENDING
20.07.26 | 29 | FAE | Between marble wall and wooden wall need silicone 4th cubicle Rhs gf vip fwr fae | 103776634 | Mechanical | PENDING
20.07.26 | 30 | FAE | Wc side cover not closing properly in multiple cubicles gf vip fwr fae | 103776129 | Mechanical | PENDING
20.07.26 | 31 | FAE | FAE basment mwr left last cubicle wc Joint SILCON REQUIRED | 103777417 | Mechanical | PENDING
20.07.26 | 32 | FAE | First floor staff MWR 2no cubicle lock need to more tight | 103777800 | Civil | PENDING
20.07.26 | 33 | FAE | GF gina MWR washbasin all sink silicon required | 103777806 | Mechanical | PENDING
20.07.26 | 34 | FAE | Soap sensor not working 3rd waterbasin gf female staff washroom fae | 103777803 | Electrical | PENDING
20.07.26 | 35 | FAE | GF apple atrium some planet pot lights not working | 103777857 | Electrical | PENDING
20.07.26 | 36 | FAE | GF vip washroom corridor near female washroom entrance celling painting required | 103777962 | Civil | PENDING
20.07.26 | 37 | FAE | FAE LG BOH near service lift 1&2 celling ac vent painting required | 103778579 | Mechanical | PENDING
20.07.26 | 38 | FAE | FAE 2nd floor HIGH-End MWR RHS 5no cubicle wc flushing button gap need to silicone | 103778613 | Mechanical | PENDING
20.07.26 | 39 | FAE | FAE P2 boh wall painting required near public elevator 1&2 boh | 103778936 | Civil | PENDING
20.07.26 | 40 | FAE | SF MLB MWR Cubicle #5 WC remote need to fixed | 103778937 | Mechanical | PENDING
20.07.26 | 41 | FAE | SF MLB MWR Cubicle #2 wall skirting need to put grouting | 103778938 | Civil | PENDING
21.07.26 | 1 | FAE | FF Infront Of Two bistro restaurant ac vent side ceiling painting required please | 103798436 | Mechanical | PENDING
21.07.26 | 2 | FAE | SF near MLB door overhead wall AC diffuser rusty requires painting | 103809150 | Mechanical | PENDING
21.07.26 | 3 | FAE | GF gina mwr urinal water senser is loose condition | 103809154 | Electrical | PENDING
21.07.26 | 4 | FAE | GF gina mwr from pod 1st cubicle corner grout need to replaced | 103809504 | Civil | PENDING
21.07.26 | 5 | FAE | GF gina mwr from pod 1st cubicle below wc gap silicone require | 103809153 | Mechanical | PENDING
21.07.26 | 6 | FAE | Fourth floor MWR underneath cabinet the drainage has bad smell coming out from it on the Left side of the wash basin counter | 103809120 | Mechanical | PENDING
21.07.26 | 7 | FAE | GF staff mwr urinal water senser not working | 103814312 | Electrical | PENDING
21.07.26 | 8 | FAE | 1st floor boh lift SE 01&02 landing area on the floor landing area floor damaged need to fix | 103817324 | Civil | PENDING
21.07.26 | 9 | FAE | 1st floor HIGH-End male washroom boh on the floor need to paint required | 103818066 | Civil | PENDING
21.07.26 | 10 | FAE | GF boh near service lift 1&2 water leaking from celling | 103818374 | Mechanical | PENDING
21.07.26 | 11 | FAE | Fourth Floor MWR POD room inside the WC seat cover detached need to fix properly | 103818482 | Mechanical | PENDING
22.07.26 | 1 | FAE | Vip lounge boh ac vent to waterleakage on going continuously | 103820520 | Mechanical | PENDING
22.07.26 | 2 | FAE | FF high-end FWR #1 BCR down the water dispenser wall tile and down baby bed wall tile both sides tiles required grouting | 103832932 | Mechanical | PENDING
22.07.26 | 3 | FAE | SF FPR Abulation Area tile coming out need to rectify please | 103831093 | Civil | PENDING
22.07.26 | 4 | FAE | Third FloorFwr Pod Skirting need to fix | 103774953 | Civil | PENDING
22.07.26 | 5 | FAE | Viplounge Janitor Corridor Ceiling Minor water dripping. |  | Mechanical | PENDING
22.07.26 | 6 | FAE | Viplounge Fwr Cabinet Door Mirror Basi Chipped . |  | Civil | PENDING
22.07.26 | 7 | FAE | Viplounge Fwr Cub no.1 Door Paint Chipped. | 103853020 | Civil | PENDING
22.07.26 | 8 | FAE | Viplounge fwr Cub no.1 Tiles Cracked. | 103853047 | Civil | PENDING
22.07.26 | 9 | FAE | SF Highend fwr RHS# Cub no.2 Wall Tiles Chipped Need to Retouch | 103853054 | Civil | PENDING
22.07.26 | 10 | FAE | FF welcome court beside information screen wall scratches and permanent stain need paint touchup | 103852837 | Civil | PENDING
22.07.26 | 11 | FAE | GF vip mwr LHS 2nd cubicle wc seat cover not working properly | 103852868 | Mechanical | PENDING
22.07.26 | 12 | FAE | SF Hi Fwr LHS# Cub no.6 Door Skirting Tiles Both Side Cracked. |  | Civil | PENDING
22.07.26 | 13 | FAE | Fourth Floor mwr inside very bad smell coming from drainage line | 103853018 | Mechanical | PENDING
22.07.26 | 14 | FAE | FF high-end mwr LHS washbasin No 4 blocked | 103853916 | Mechanical | PENDING
22.07.26 | 15 | FAE | Blvd mwr strong bed smell coming from urinals pls require chemical wash tonight | 103854356 | Mechanical | PENDING
22.07.26 | 16 | FAE | 3rd fl Fwr Corridor Cub no. 3 Wall Grouting requirements | 103854373 | Civil | PENDING
22.07.26 | 17 | FAE | LG transguard pantry badsmelling | 103857030 | Civil | PENDING
Note on G514: Source report had a blank status for this item; defaulted to PENDING.